## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 – Setup & Extraction | S1 | US-01 | As a student, I want to fetch tweets by username so that I can analyze engagement. | Must | Twitter API credentials, tweepy |  | Done
S1 – Setup & Extraction | S1 | US-02 | As a user, I want raw tweets saved to JSON so I can use them later in analysis. | Must | Filesystem write permissions |  | Done
S2 – Sentiment & Scoring | S2 | US-03 | As an analyst, I want to run sentiment and engagement scoring for each tweet. | Must | Gemini API key, run_prompt.py |  | Done
S2 – Sentiment & Scoring | S2 | US-04 | As an analyst, I want analyzed results saved as analyzed_tweets.json for reuse. | Should | JSON schema from execute_gemini() |  | Done
S3 – Generation & Comparison | S3 | US-05 | As a marketer, I want two candidate tweets (A/B) generated from examples and a prompt. | Must | create_tweet.py, top_5_selection() |  | Done
S3 – Generation & Comparison | S3 | US-06 | As a user, I want an AI prediction of which tweet will perform better and why. | Should | execute_gemini_for_tweet_prediction() |  | Done
S3 – Simple UI | S3 | US-07 | As a user, I want a simple page to enter a prompt and view tweets and prediction. | Could | index.html, /generate endpoint |  | Done
S3 – Posting | S3 | US-08 | As a user, I want to post Tweet A or B from the UI to Twitter (or mock). | Won't (now) | Backend /tweet route, Twitter write access |  | Done
S2 – QA & Reliability | S2 | US-09 | As a developer, I want basic error handling for invalid credentials and rate limits. | Should | tweepy exceptions, try/except |  | Done
S1 – Config | S1 | US-10 | As a developer, I want secrets read from environment variables to keep them safe. | Could | dotenv / os.environ refactor |  | TODO
Note on F1: : ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: : ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: : ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on K3: : ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: : ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: : ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: : ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: : ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: : ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: : ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: : ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: : ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: : ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: : ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: : ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: : ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on I3: : ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: : ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7